## Bug Summary
BUG REPORT SUMMARY
E-Commerce Web Application - shop.qaautomationlabs.com
Report Generated: 2026-03-08 19:20
Prepared By: Chinonso Nwosu ¦ QA Engineer
DEFECT STATISTICS
Total Bugs Reported | 15
Critical | 2
High | 4
Medium | 5
Low | 4
Open | 6
In Progress | 3
Fixed (Pending Verification) | 4
Closed | 2
DEFECTS BY MODULE
Module | Critical | High | Medium | Low | Total
Authentication | 0 | 1 | 1 | 1 | 3
Product Search | 0 | 0 | 1 | 2 | 3
Shopping Cart | 2 | 1 | 1 | 0 | 4
Checkout | 0 | 1 | 1 | 0 | 2
User Account | 0 | 1 | 1 | 1 | 3
SEVERITY DEFINITIONS
Critical | Application crash, data loss, security breach, or complete feature failure blocking core functionality
High | Major feature not working, significant impact on user experience, no workaround available
Medium | Feature partially working, workaround available, moderate impact on user experience
Low | Minor issue, cosmetic defect, minimal impact on functionality

## Detailed Bug Reports
Bug ID | Title | Module | Severity | Priority | Status | Reported By | Reported Date | Assigned To | Environment | Browser/Device | Steps to Reproduce | Expected Result | Actual Result | Attachments | Notes
BUG-001 | Shopping Cart Total Not Updating After Quantity Change | Shopping Cart | Critical | P1 | Open | Chinonso Nwosu | 2024-01-15 | Dev Team | Production | Chrome 120, Windows 11 | 1. Navigate to shop.qaautomationlabs.com 2. Browse any product and click 'Add to Cart' 3. Go to the cart page via cart icon 4. Change the quantity field from 1 to 3 5. Click 'Update Cart' or tab out of field 6. Observe the cart subtotal and total | Cart subtotal should update to reflect 3x the product price (e.g., $50 item × 3 = $150 subtotal) | Cart subtotal remains unchanged showing price for 1 item only ($50). The quantity visually updates to 3 but total stays at $50. Issue persists after page refresh. | screenshot_bug001_cart.png video_bug001_repro.mp4 | BLOCKER for checkout flow. Users cannot purchase multiple quantities. Verified on multiple browsers. Backend API returns correct total but frontend doesn't update.
BUG-002 | Payment Processing Fails Silently on Timeout | Shopping Cart | Critical | P1 | In Progress | Chinonso Nwosu | 2024-01-18 | Backend Team | Staging | All Browsers | 1. Add items to cart totaling over $500 2. Proceed to checkout 3. Enter valid shipping information 4. Enter valid test card (4111111111111111) 5. Simulate slow network (Chrome DevTools: Slow 3G) 6. Click 'Place Order' | Either successful order confirmation OR clear error message explaining the payment issue | Spinner shows indefinitely (3+ minutes), then page becomes unresponsive. No error message displayed. Refreshing page shows empty cart. Backend logs show timeout but no user notification. | screenshot_bug002_spinner.png network_log_bug002.har | Potential duplicate charges reported by test users. Critical UX issue - users don't know if order went through.
BUG-003 | Login Form Accepts Empty Password Field | Authentication | High | P2 | Open | Chinonso Nwosu | 2024-01-12 | Dev Team | Production | All Browsers | 1. Navigate to login page (shop.qaautomationlabs.com/login) 2. Enter valid registered email address 3. Leave password field completely empty 4. Click 'Sign In' button | Client-side validation should trigger immediately with error message: 'Password is required' | Form submits to server without validation. After 2-3 second delay, generic 'Login failed' error appears from server response. This exposes unnecessary server requests. | screenshot_bug003_validation.png | Security concern - client-side validation missing. Creates unnecessary server load. Should implement HTML5 required attribute and JS validation.
BUG-004 | Add to Cart Button Unresponsive on First Click | Shopping Cart | High | P2 | Fixed | Chinonso Nwosu | 2024-01-10 | Frontend Team | Production | Safari 17, iOS 17 | 1. Open product detail page on Safari iOS 2. Wait for page to fully load 3. Tap 'Add to Cart' button immediately 4. Observe button state and cart icon | Product should be added to cart on first tap with visual feedback (button state change, cart badge update) | First tap does nothing - no visual feedback, no cart update. Second tap works correctly. Issue appears to be JavaScript initialization race condition. | video_bug004_ios_tap.mov | Affects approximately 18% of users (iOS Safari). May relate to lazy loading of cart JS module. Fixed in build 2.3.1
BUG-005 | Checkout Shipping Address Not Validating ZIP Code Format | Checkout | High | P2 | Open | Chinonso Nwosu | 2024-01-20 | Dev Team | Production | Chrome 120, Firefox 121 | 1. Add item to cart and proceed to checkout 2. Fill shipping form with valid data 3. Enter invalid ZIP code format (e.g., 'ABCDE' or '123') 4. Click 'Continue to Shipping Method' | Validation error: 'Please enter a valid ZIP code (e.g., 12345 or 12345-6789)' | Form accepts any input in ZIP field. Proceeds to shipping method selection. Error only appears at final order submission, forcing user to go back and fix. | screenshot_bug005_zip.png | UX issue - validation should happen inline on field blur, not at end of flow. Can cause shipping calculation errors.
BUG-006 | User Profile Changes Not Persisting After Save | User Account | High | P2 | In Progress | Chinonso Nwosu | 2024-01-19 | Backend Team | Production | All Browsers | 1. Login to account 2. Go to My Account > Profile 3. Change first name from 'John' to 'Jonathan' 4. Click 'Save Changes' 5. Success message appears 6. Refresh page or navigate away and return | Profile should display updated name 'Jonathan' after save and persist after refresh | Success message shows 'Profile updated successfully' but refreshing page reverts to original name 'John'. Changes not persisted to database. | video_bug006_profile.mp4 api_response_bug006.json | API returns 200 OK but database not updated. Likely caching issue or transaction rollback. Affects all profile fields.
BUG-007 | Product Images Not Loading on Category Page | Product Search | Medium | P3 | Open | Chinonso Nwosu | 2024-01-14 | Dev Team | Production | Firefox 121, macOS Sonoma | 1. Navigate to shop.qaautomationlabs.com/category/electronics 2. Wait for page to fully load 3. Scroll through the product listing 4. Observe product thumbnail images | All product images should load and display correctly within 3 seconds of entering viewport | Approximately 30% of product images show broken image placeholder (gray box with broken image icon). Console shows 404 errors for these image URLs. Pattern seems random. | screenshot_bug007_broken_images.png console_log_bug007.txt | CDN issue suspected. Some image paths have incorrect format. Workaround: hard refresh sometimes loads images.
BUG-008 | Search Results Count Mismatch | Product Search | Medium | P3 | Fixed | Chinonso Nwosu | 2024-01-11 | Backend Team | Production | Safari 17, iOS | 1. Enter 'laptop' in search field 2. Press Enter or click search icon 3. Observe the results count message at top 4. Manually count the actual products displayed on page | Results count message should accurately reflect the number of products shown | Message says '15 results found' but only 12 products are displayed on page. Pagination shows only 1 page. 3 products missing from display. | screenshot_bug008_count.png | Backend returns 15 results but 3 are filtered out on frontend due to inventory status. Count should reflect visible products only. Fixed in v2.3.2
BUG-009 | Coupon Code Field Case Sensitive | Shopping Cart | Medium | P3 | Open | Chinonso Nwosu | 2024-01-16 | Dev Team | Production | All Browsers | 1. Add items to cart 2. Enter coupon code 'save10' (lowercase) 3. Click Apply 4. Try again with 'SAVE10' (uppercase) | Coupon codes should be case-insensitive. Both 'save10' and 'SAVE10' should apply the same discount | 'save10' returns 'Invalid coupon code' error. Only 'SAVE10' (exact case) works. Users often type lowercase leading to confusion. | screenshot_bug009_coupon.png | Backend validation is case-sensitive. Should normalize to uppercase before validation. Common UX improvement.
BUG-010 | Order Confirmation Email Delayed by 30+ Minutes | Checkout | Medium | P3 | In Progress | Chinonso Nwosu | 2024-01-17 | Backend Team | Production | N/A - Email | 1. Complete a successful order 2. Note the order confirmation time 3. Check email inbox for confirmation 4. Record time when email arrives | Order confirmation email should arrive within 2-5 minutes of order completion | Confirmation emails consistently arrive 30-45 minutes after order. Some users report not receiving email at all (checked spam). | email_timestamps_bug010.xlsx | Email queue processing issue. May be related to third-party email service. Users calling support thinking order failed.
BUG-011 | Password Visibility Toggle Not Working | Authentication | Medium | P3 | Fixed | Chinonso Nwosu | 2024-01-13 | Frontend Team | Production | Edge 120, Windows 11 | 1. Go to login or registration page 2. Enter text in password field 3. Click the eye icon to show password 4. Observe password field | Password should toggle between hidden (dots) and visible (plain text) when eye icon is clicked | Eye icon appears clickable but nothing happens on click. Password remains hidden. No JavaScript errors in console. | video_bug011_toggle.mp4 | Event listener not attached to icon element. Quick fix applied. Fixed in hotfix 2.3.0-hf1
BUG-012 | Footer Links Misaligned on Tablet View | User Account | Low | P4 | Open | Chinonso Nwosu | 2024-01-09 | Frontend Team | Production | iPad Safari, 768px width | 1. Open website on iPad or resize browser to 768px width 2. Scroll to footer 3. Observe footer link columns | Footer columns should be evenly spaced and properly aligned in 2-column or 3-column layout | Footer columns overlap slightly. 'Customer Service' and 'About Us' columns have 5px overlap causing text to touch. Only at exactly 768px breakpoint. | screenshot_bug012_footer.png | CSS media query edge case. Low priority cosmetic issue. Workaround: zoom in/out slightly.
BUG-013 | Product Rating Stars Display Incorrectly for Half Values | Product Search | Low | P4 | Closed | Chinonso Nwosu | 2024-01-08 | Frontend Team | Production | All Browsers | 1. Find product with 3.5 star rating 2. Observe the star rating display | Should show 3 full stars, 1 half star, and 1 empty star | Shows 3 full stars and 2 empty stars (rounds down). Half-star icon not rendering. | screenshot_bug013_stars.png | SVG half-star icon path was incorrect. Fixed and verified in v2.2.9
BUG-014 | Breadcrumb Navigation Shows Encoded Characters | User Account | Low | P4 | Open | Chinonso Nwosu | 2024-01-21 | Frontend Team | Production | All Browsers | 1. Navigate to a category with special characters (e.g., 'Men's Clothing') 2. Observe the breadcrumb trail | Breadcrumb should show: Home > Men's Clothing | Breadcrumb shows: Home > Men%27s%20Clothing (URL encoded) | screenshot_bug014_breadcrumb.png | Frontend not decoding URL parameters for display. Cosmetic issue only - navigation still works correctly.
BUG-015 | Newsletter Popup Shows on Every Page Visit | Product Search | Low | P4 | Closed | Chinonso Nwosu | 2024-01-07 | Frontend Team | Production | Chrome 120, Incognito Mode | 1. Visit homepage in normal mode 2. Close newsletter popup 3. Navigate to another page 4. Popup appears again | Newsletter popup should only appear once per session (cookie-based) or once per user | Popup appears on every page navigation. Cookie not being set correctly. Extremely disruptive UX. | video_bug015_popup.mp4 | Cookie path was set incorrectly. Fixed in v2.3.0. Verified closed.

## Bug Report Template
BUG REPORT TEMPLATE
Use this template for consistent bug reporting
FIELD | DESCRIPTION | EXAMPLE
Bug ID | Unique identifier (auto-generated or manual) | BUG-016
Title | Clear, concise summary of the issue (max 100 chars) | Login button unresponsive on mobile Safari
Module | Application area affected | Authentication / Cart / Checkout / Search / Account
Severity | Impact level of the bug | Critical / High / Medium / Low
Priority | Fix urgency | P1 (Immediate) / P2 (High) / P3 (Medium) / P4 (Low)
Status | Current state | Open / In Progress / Fixed / Closed / Reopened
Reported By | Name of person who found the bug | Chinonso Nwosu
Reported Date | Date bug was logged | 2024-01-22
Assigned To | Developer/team responsible for fix | Frontend Team
Environment | Where bug was found | Production / Staging / Development
Browser/Device | Specific browser version and OS | Chrome 120, Windows 11 / Safari 17, iOS 17.2
Steps to Reproduce | Numbered steps to recreate the bug | 1. Go to page X 2. Click button Y 3. Observe result Z
Expected Result | What should happen | User should see confirmation message
Actual Result | What actually happens (the bug) | Error 500 displayed, no confirmation
Attachments | Screenshots, videos, logs | screenshot.png, console_log.txt
Notes | Additional context, workarounds, related bugs | Similar to BUG-005. Workaround: use Firefox
BUG REPORTING BEST PRACTICES
1. One bug per report - Don't combine multiple issues
2. Be specific - Include exact error messages, URLs, and data used
3. Reproduce before reporting - Confirm the bug happens consistently
4. Include visual evidence - Screenshots and videos save debugging time
5. Check for duplicates - Search existing bugs before creating new ones
6. Use clear titles - Other team members should understand the issue from the title
7. Include environment details - OS, browser, screen size all matter
8. Describe workarounds - If you found one, include it
9. Update status - Keep the bug status current as it progresses
10. Verify fixes - Test the fix and close only when fully resolved

## Defect Metrics
DEFECT METRICS DASHBOARD
Reporting Period: January 2024
KEY METRICS
Metric | Value | Target | Status
Total Defects Found | 15 | - | N/A
Defects Fixed | 6 | - | 40%
Defect Detection Rate | 2.5 per day | 2.0 | Above Target
Average Resolution Time | 3.2 days | 5 days | On Track
Critical Bug Resolution Time | 1.5 days | 1 day | Needs Improvement
Defect Leakage Rate | 2% | <5% | On Track
Reopen Rate | 8% | <10% | On Track
WEEKLY TREND
Week | New Bugs | Resolved | Open (End of Week)
Week 1 (Jan 1-7) | 4 | 2 | 2
Week 2 (Jan 8-14) | 5 | 3 | 4
Week 3 (Jan 15-21) | 6 | 1 | 9
Week 4 (Jan 22-28) | 0 | 3 | 6