## Test Plan
TEST PLAN
E-Commerce Web Application Testing
Application Under Test: shop.qaautomationlabs.com
Document Version: | 1.0
Created By: | Chinonso Nwosu
Creation Date: | 2026-03-08
Last Updated: | 2026-03-08
Status: | Final
1. INTRODUCTION
This test plan outlines the testing strategy, scope, approach, and schedule for the e-commerce web application at shop.qaautomationlabs.com.
The document serves as a guide for the QA team to ensure comprehensive testing coverage and quality assurance.
2. SCOPE
In Scope:
• User Registration and Authentication (Login, Logout, Password Reset)
• Product Catalog (Search, Filter, Sort, Product Details)
• Shopping Cart (Add, Remove, Update Quantities)
• Checkout Process (Shipping, Payment, Order Confirmation)
• User Account Management (Profile, Order History, Address Book)
Out of Scope:
• Payment gateway integration (using test/sandbox mode)
• Performance and load testing
• Mobile application testing
3. TEST OBJECTIVES
• Verify all functional requirements are implemented correctly
• Identify and document defects before production release
• Ensure the application meets usability standards
• Validate data integrity across all user flows
• Confirm cross-browser compatibility (Chrome, Firefox, Edge)
• Verify responsive design on different screen sizes
4. TEST STRATEGY
Testing Types:
• Smoke Testing: Verify critical paths after each build
• Functional Testing: Validate all features against requirements
• Regression Testing: Ensure new changes don't break existing functionality
• Integration Testing: Verify component interactions
• User Acceptance Testing: Validate business requirements
Testing Approach:
• Manual testing for exploratory and usability testing
• Automated testing for regression test suites (Cypress)
• API testing for backend validation (Postman)
5. ENTRY CRITERIA
• Test environment is set up and accessible
• Test data is prepared and loaded
• Build is deployed to test environment
• All critical/blocker defects from previous build are fixed
• Test cases are reviewed and approved
• Required access credentials are available
6. EXIT CRITERIA
• All planned test cases are executed
• 95% of test cases pass
• No critical or high severity defects remain open
• All medium severity defects are documented with workarounds
• Test summary report is completed and approved
• Sign-off from stakeholders
7. RISK ASSESSMENT
¦ Risk ¦ Probability ¦ Impact ¦ Mitigation ¦
¦ Test environment instability ¦ Medium ¦ High ¦ Backup environment, close coordination with DevOps ¦
¦ Incomplete requirements ¦ Low ¦ High ¦ Regular sync with product team, document assumptions ¦
¦ Resource unavailability ¦ Low ¦ Medium ¦ Cross-training, documentation of test procedures ¦
¦ Third-party service downtime ¦ Medium ¦ Medium ¦ Mock services for testing, scheduled test windows ¦
¦ Scope creep ¦ Medium ¦ Medium ¦ Change control process, impact analysis ¦
8. TEST DELIVERABLES
• Test Plan (this document)
• Test Cases with detailed steps
• Requirements Traceability Matrix
• Bug Reports with severity and priority
• Test Execution Reports
• Test Summary Report
9. RESOURCE ALLOCATION
¦ Role ¦ Responsibility ¦
¦ QA Engineer ¦ Test case design, execution, defect reporting ¦
¦ QA Lead ¦ Test planning, review, coordination ¦
¦ Developer ¦ Defect fixes, technical support ¦
¦ Product Owner ¦ Requirements clarification, UAT sign-off ¦
10. SCHEDULE
¦ Phase ¦ Duration ¦ Activities ¦
¦ Test Planning ¦ 2 days ¦ Create test plan, identify test scenarios ¦
¦ Test Case Design ¦ 3 days ¦ Write detailed test cases, review ¦
¦ Test Environment Setup ¦ 1 day ¦ Configure environment, prepare test data ¦
¦ Test Execution Cycle 1 ¦ 5 days ¦ Execute all test cases ¦
¦ Defect Fixing ¦ 3 days ¦ Development fixes reported defects ¦
¦ Regression Testing ¦ 2 days ¦ Verify fixes, run regression suite ¦
¦ UAT ¦ 2 days ¦ Business validation and sign-off ¦

## Test Cases
Test ID | Module | Title | Priority | Preconditions | Test Steps | Expected Result | Actual Result | Status | Notes
TC-AUTH-001 | Authentication | Verify successful user registration with valid data | High | User is on registration page | 1. Enter valid first name 2. Enter valid last name 3. Enter valid email 4. Enter valid password (8+ chars, uppercase, number) 5. Confirm password 6. Click Register button | User is registered successfully and redirected to account page with welcome message | As expected | Pass
TC-AUTH-002 | Authentication | Verify registration fails with existing email | High | User is on registration page, email already exists in system | 1. Enter valid first name 2. Enter valid last name 3. Enter existing email 4. Enter valid password 5. Click Register | Error message displayed: 'Email already registered' | As expected | Pass
TC-AUTH-003 | Authentication | Verify registration fails with invalid email format | High | User is on registration page | 1. Enter 'invalidemail' in email field 2. Click outside the field | Validation error: 'Please enter a valid email address' | As expected | Pass
TC-AUTH-004 | Authentication | Verify registration fails with weak password | High | User is on registration page | 1. Enter valid email 2. Enter password '123' 3. Click Register | Error: 'Password must be at least 8 characters with uppercase and number' | As expected | Pass
TC-AUTH-005 | Authentication | Verify registration fails with mismatched passwords | Medium | User is on registration page | 1. Enter password 'Password123' 2. Enter confirm password 'Password456' 3. Click Register | Error: 'Passwords do not match' | As expected | Pass
TC-AUTH-006 | Authentication | Verify successful login with valid credentials | Critical | User has a registered account | 1. Navigate to login page 2. Enter valid email 3. Enter valid password 4. Click Login | User is logged in and redirected to homepage with account menu visible | As expected | Pass
TC-AUTH-007 | Authentication | Verify login fails with incorrect password | High | User has a registered account | 1. Navigate to login page 2. Enter valid email 3. Enter incorrect password 4. Click Login | Error: 'Invalid email or password' | As expected | Pass
TC-AUTH-008 | Authentication | Verify login fails with non-existent email | High | User is on login page | 1. Enter non-existent email 2. Enter any password 3. Click Login | Error: 'Invalid email or password' | As expected | Pass
TC-AUTH-009 | Authentication | Verify login fails with empty fields | Medium | User is on login page | 1. Leave email field empty 2. Leave password field empty 3. Click Login | Validation errors shown for both fields | As expected | Pass
TC-AUTH-010 | Authentication | Verify Remember Me functionality | Low | User has a registered account | 1. Login with valid credentials 2. Check 'Remember Me' 3. Close browser 4. Reopen and navigate to site | User remains logged in | As expected | Pass
TC-AUTH-011 | Authentication | Verify successful logout | High | User is logged in | 1. Click on account menu 2. Click Logout | User is logged out and redirected to homepage, login option visible | As expected | Pass
TC-AUTH-012 | Authentication | Verify password reset email is sent | High | User has a registered account | 1. Click 'Forgot Password' 2. Enter registered email 3. Click Submit | Success message: 'Password reset link sent to your email' | As expected | Pass
TC-AUTH-013 | Authentication | Verify password reset with invalid email | Medium | User is on forgot password page | 1. Enter non-existent email 2. Click Submit | Error: 'Email not found in our system' | As expected | Pass
TC-AUTH-014 | Authentication | Verify session timeout after inactivity | Medium | User is logged in | 1. Login to account 2. Leave browser idle for 30 minutes 3. Try to access protected page | User is redirected to login page with session expired message | Not tested | Blocked | Requires extended wait time
TC-AUTH-015 | Authentication | Verify concurrent login from multiple devices | Low | User has a registered account | 1. Login from Device A 2. Login from Device B with same credentials 3. Check session on Device A | Both sessions remain active (or based on business rule) | As expected | Pass
TC-SRCH-001 | Product Search | Verify search returns relevant products | High | User is on homepage | 1. Enter 'laptop' in search box 2. Click search or press Enter | Search results display products containing 'laptop' in title or description | As expected | Pass
TC-SRCH-002 | Product Search | Verify search with no results | Medium | User is on homepage | 1. Enter 'xyznonexistent123' in search box 2. Click search | Message displayed: 'No products found for your search' | As expected | Pass
TC-SRCH-003 | Product Search | Verify search with special characters | Medium | User is on homepage | 1. Enter '@#$%' in search box 2. Click search | No results or handled gracefully without errors | As expected | Pass
TC-SRCH-004 | Product Search | Verify search is case-insensitive | Medium | User is on homepage | 1. Search 'LAPTOP' 2. Search 'laptop' 3. Compare results | Both searches return same results | As expected | Pass
TC-SRCH-005 | Product Search | Verify search suggestions appear | Low | User is on homepage | 1. Start typing 'lap' in search box | Autocomplete suggestions appear with matching products | As expected | Pass
TC-SRCH-006 | Product Search | Verify category filter works | High | User is on product listing page | 1. Select 'Electronics' category from filter | Only products in Electronics category are displayed | As expected | Pass
TC-SRCH-007 | Product Search | Verify multiple category selection | Medium | User is on product listing page | 1. Select 'Electronics' 2. Also select 'Accessories' | Products from both categories are displayed | As expected | Pass
TC-SRCH-008 | Product Search | Verify price range filter - minimum | High | User is on product listing page | 1. Set minimum price to $50 2. Apply filter | Only products priced $50 or above are displayed | As expected | Pass
TC-SRCH-009 | Product Search | Verify price range filter - maximum | High | User is on product listing page | 1. Set maximum price to $100 2. Apply filter | Only products priced $100 or below are displayed | As expected | Pass
TC-SRCH-010 | Product Search | Verify price range filter - both min and max | High | User is on product listing page | 1. Set min price $50 2. Set max price $100 3. Apply filter | Only products priced between $50-$100 are displayed | As expected | Pass
TC-SRCH-011 | Product Search | Verify sort by price low to high | High | User is on product listing page with multiple products | 1. Select 'Price: Low to High' from sort dropdown | Products are reordered with lowest price first | As expected | Pass
TC-SRCH-012 | Product Search | Verify sort by price high to low | High | User is on product listing page | 1. Select 'Price: High to Low' from sort dropdown | Products are reordered with highest price first | As expected | Pass
TC-SRCH-013 | Product Search | Verify sort by name A-Z | Medium | User is on product listing page | 1. Select 'Name: A to Z' from sort dropdown | Products are sorted alphabetically A-Z | As expected | Pass
TC-SRCH-014 | Product Search | Verify sort by newest arrivals | Medium | User is on product listing page | 1. Select 'Newest' from sort dropdown | Products are sorted by date added, newest first | As expected | Pass
TC-SRCH-015 | Product Search | Verify filter by brand | High | User is on product listing page | 1. Select brand 'Apple' from brand filter | Only Apple products are displayed | As expected | Pass
TC-SRCH-016 | Product Search | Verify filter combination works | High | User is on product listing page | 1. Select category 'Electronics' 2. Set price $100-$500 3. Select brand 'Samsung' 4. Apply filters | Only Samsung Electronics priced $100-$500 displayed | As expected | Pass
TC-SRCH-017 | Product Search | Verify clear all filters | Medium | User has applied multiple filters | 1. Click 'Clear All Filters' button | All filters removed, all products displayed | As expected | Pass
TC-SRCH-018 | Product Search | Verify pagination on search results | Medium | Search returns more than 20 products | 1. Search for common term 2. Scroll to bottom 3. Click page 2 | Next page of results loads correctly | As expected | Pass
TC-SRCH-019 | Product Search | Verify products per page selection | Low | User is on product listing page | 1. Change 'Show' dropdown from 20 to 50 | 50 products displayed per page | As expected | Pass
TC-SRCH-020 | Product Search | Verify filter count displays correctly | Low | User is on product listing page | 1. Apply category filter 2. Check product count | Count shows correct number matching filter criteria | As expected | Pass
TC-CART-001 | Shopping Cart | Verify add single product to cart | Critical | User is on product detail page | 1. Click 'Add to Cart' button | Product added to cart, cart icon shows 1 item, success message displayed | As expected | Pass
TC-CART-002 | Shopping Cart | Verify add product with quantity | High | User is on product detail page | 1. Set quantity to 3 2. Click 'Add to Cart' | 3 units added to cart, cart total updates correctly | As expected | Pass
TC-CART-003 | Shopping Cart | Verify cart icon badge updates | High | Cart is empty | 1. Add product A 2. Add product B 3. Check cart icon | Cart icon shows '2' indicating 2 items | As expected | Pass
TC-CART-004 | Shopping Cart | Verify cart displays correct products | Critical | User has added products to cart | 1. Click cart icon 2. View cart page | All added products displayed with correct names, prices, quantities | As expected | Pass
TC-CART-005 | Shopping Cart | Verify update quantity in cart | Critical | User has product in cart | 1. Go to cart 2. Change quantity from 1 to 5 3. Click Update | Quantity updates to 5, subtotal recalculates correctly | Error: Total not updating | Fail | BUG-001 logged
TC-CART-006 | Shopping Cart | Verify remove item from cart | High | User has products in cart | 1. Go to cart 2. Click 'Remove' on a product | Product removed from cart, totals update | As expected | Pass
TC-CART-007 | Shopping Cart | Verify cart persists after logout/login | Medium | Logged in user has items in cart | 1. Add products to cart 2. Logout 3. Login again 4. Check cart | Cart items are preserved after re-login | As expected | Pass
TC-CART-008 | Shopping Cart | Verify cart total calculation | Critical | User has multiple products in cart | 1. Add Product A ($50) x2 2. Add Product B ($30) x1 3. Check subtotal | Subtotal shows $130 (50*2 + 30*1) | As expected | Pass
TC-CART-009 | Shopping Cart | Verify empty cart message | Medium | User has empty cart | 1. Go to cart page | Message: 'Your cart is empty' with link to continue shopping | As expected | Pass
TC-CART-010 | Shopping Cart | Verify add same product twice | Medium | User has Product A in cart | 1. Go to Product A page 2. Add to cart again | Quantity of Product A increases instead of duplicate entry | As expected | Pass
TC-CART-011 | Shopping Cart | Verify max quantity limit | Medium | User is on product page | 1. Set quantity to 9999 2. Add to cart | Error message if exceeds stock or reasonable limit | As expected | Pass
TC-CART-012 | Shopping Cart | Verify cart with out-of-stock product | High | Product in cart goes out of stock | 1. Add product 2. Product becomes out of stock 3. View cart | Warning message shown, checkout blocked or item marked | As expected | Pass
TC-CART-013 | Shopping Cart | Verify apply valid coupon code | High | User has items in cart, valid coupon exists | 1. Enter coupon 'SAVE10' 2. Click Apply | 10% discount applied, totals update | As expected | Pass
TC-CART-014 | Shopping Cart | Verify apply invalid coupon code | Medium | User has items in cart | 1. Enter invalid coupon 'FAKECODE' 2. Click Apply | Error: 'Invalid coupon code' | As expected | Pass
TC-CART-015 | Shopping Cart | Verify apply expired coupon code | Medium | User has items in cart, coupon is expired | 1. Enter expired coupon code 2. Click Apply | Error: 'This coupon has expired' | As expected | Pass
TC-CART-016 | Shopping Cart | Verify remove coupon code | Low | User has coupon applied | 1. Click 'Remove' next to coupon | Coupon removed, original prices restored | As expected | Pass
TC-CART-017 | Shopping Cart | Verify cart updates with price change | Medium | User has item in cart, price changes | 1. Add product at $50 2. Admin changes price to $60 3. Refresh cart | Cart reflects new price $60 | As expected | Pass
TC-CART-018 | Shopping Cart | Verify Continue Shopping link | Low | User is on cart page | 1. Click 'Continue Shopping' | User redirected to product listing or homepage | As expected | Pass
TC-CHKT-001 | Checkout | Verify checkout button is accessible | Critical | User has items in cart | 1. Go to cart 2. Click 'Proceed to Checkout' | User navigates to checkout page | As expected | Pass
TC-CHKT-002 | Checkout | Verify guest checkout option | High | User is not logged in, has items in cart | 1. Click Checkout 2. Select 'Continue as Guest' | Guest can proceed without creating account | As expected | Pass
TC-CHKT-003 | Checkout | Verify shipping address form validation | High | User is on checkout shipping step | 1. Leave all fields empty 2. Click Continue | Validation errors shown for all required fields | As expected | Pass
TC-CHKT-004 | Checkout | Verify valid shipping address accepted | Critical | User is on checkout shipping step | 1. Fill all fields with valid data 2. Click Continue | Address saved, user proceeds to shipping method | As expected | Pass
TC-CHKT-005 | Checkout | Verify shipping method selection | High | User completed shipping address | 1. View shipping options 2. Select 'Express Shipping' | Shipping cost updates, express option selected | As expected | Pass
TC-CHKT-006 | Checkout | Verify shipping cost calculation | High | User is selecting shipping method | 1. Select Standard ($5) 2. Check order total | Order total includes $5 shipping | As expected | Pass
TC-CHKT-007 | Checkout | Verify free shipping threshold | Medium | Cart subtotal is above free shipping threshold ($100) | 1. Add items totaling $150 2. Go to checkout | Free shipping option available | As expected | Pass
TC-CHKT-008 | Checkout | Verify payment methods displayed | High | User is on payment step | 1. View payment options | Credit Card, PayPal, and other configured methods shown | As expected | Pass
TC-CHKT-009 | Checkout | Verify credit card form validation | Critical | User selects Credit Card payment | 1. Enter invalid card number '1234' 2. Click Pay | Error: 'Invalid card number' | As expected | Pass
TC-CHKT-010 | Checkout | Verify credit card expiry validation | High | User is entering card details | 1. Enter expired date (past month/year) 2. Submit | Error: 'Card has expired' | As expected | Pass
TC-CHKT-011 | Checkout | Verify CVV validation | High | User is entering card details | 1. Enter 2-digit CVV 2. Submit | Error: 'Invalid CVV' | As expected | Pass
TC-CHKT-012 | Checkout | Verify successful payment with valid card | Critical | User has valid test card details | 1. Enter valid test card 4111111111111111 2. Enter valid expiry 3. Enter valid CVV 4. Submit | Payment processed, order confirmed | As expected | Pass | Test card used
TC-CHKT-013 | Checkout | Verify order confirmation page | Critical | User completed successful checkout | 1. Complete payment | Order confirmation page shows order number, items, total, shipping address | As expected | Pass
TC-CHKT-014 | Checkout | Verify order confirmation email | High | User completed checkout with email | 1. Complete order 2. Check email inbox | Confirmation email received with order details | As expected | Pass
TC-CHKT-015 | Checkout | Verify order appears in order history | High | Logged in user completed order | 1. Complete order 2. Go to My Account > Orders | New order visible in order history | As expected | Pass
TC-CHKT-016 | Checkout | Verify billing address same as shipping | Medium | User is on payment step | 1. Check 'Billing same as shipping' 2. Complete payment | Billing address auto-filled from shipping | As expected | Pass
TC-CHKT-017 | Checkout | Verify different billing address | Medium | User is on payment step | 1. Uncheck 'Billing same as shipping' 2. Enter different billing address 3. Complete | Order placed with different billing address | As expected | Pass
TC-CHKT-018 | Checkout | Verify order total matches cart total | Critical | User has items in cart | 1. Note cart total 2. Proceed to checkout 3. Compare order total | Order total equals cart subtotal + shipping + tax | As expected | Pass
TC-CHKT-019 | Checkout | Verify tax calculation | High | User enters shipping address with tax | 1. Enter address in taxable region 2. View order summary | Tax calculated and displayed correctly | As expected | Pass
TC-CHKT-020 | Checkout | Verify back button preserves data | Medium | User is on payment step with filled shipping | 1. Click Back to shipping step 2. Check shipping form | Previously entered data is preserved | As expected | Pass
TC-CHKT-021 | Checkout | Verify declined card handling | High | User has declined test card | 1. Enter declined test card number 2. Submit payment | Error: 'Payment declined. Please try another card.' | As expected | Pass
TC-CHKT-022 | Checkout | Verify checkout with empty cart | Medium | User has empty cart | 1. Navigate directly to checkout URL | Redirected to cart with message 'Your cart is empty' | As expected | Pass
TC-CHKT-023 | Checkout | Verify Save shipping address for logged user | Medium | Logged in user on checkout | 1. Check 'Save this address' 2. Complete order 3. Check account addresses | Address saved to account address book | As expected | Pass
TC-CHKT-024 | Checkout | Verify select saved address | Medium | Logged in user has saved addresses | 1. Go to checkout 2. Select from saved addresses dropdown | Address fields auto-populated | As expected | Pass
TC-CHKT-025 | Checkout | Verify print order confirmation | Low | User on order confirmation page | 1. Click 'Print' button | Print dialog opens with formatted order details | As expected | Pass
TC-ACCT-001 | Account | Verify view account dashboard | High | User is logged in | 1. Click 'My Account' | Account dashboard displays with user info, recent orders, quick links | As expected | Pass
TC-ACCT-002 | Account | Verify update profile information | High | User is on account page | 1. Edit first name to 'NewName' 2. Click Save | Profile updated, success message shown | As expected | Pass
TC-ACCT-003 | Account | Verify change password | High | User is on account settings | 1. Enter current password 2. Enter new password 3. Confirm new password 4. Save | Password changed, confirmation message shown | As expected | Pass
TC-ACCT-004 | Account | Verify change password with wrong current | Medium | User is on account settings | 1. Enter incorrect current password 2. Enter new password 3. Save | Error: 'Current password is incorrect' | As expected | Pass
TC-ACCT-005 | Account | Verify add new address | Medium | User is on address book page | 1. Click 'Add New Address' 2. Fill all fields 3. Save | New address added to address book | As expected | Pass
TC-ACCT-006 | Account | Verify edit existing address | Medium | User has saved address | 1. Click Edit on address 2. Modify city 3. Save | Address updated with new city | As expected | Pass
TC-ACCT-007 | Account | Verify delete address | Medium | User has multiple saved addresses | 1. Click Delete on an address 2. Confirm deletion | Address removed from address book | As expected | Pass
TC-ACCT-008 | Account | Verify set default address | Low | User has multiple addresses | 1. Click 'Set as Default' on an address | Address marked as default, shown first in checkout | As expected | Pass
TC-ACCT-009 | Account | Verify view order history | High | User has placed orders | 1. Go to My Account > Orders | List of all orders with dates, totals, status | As expected | Pass
TC-ACCT-010 | Account | Verify view order details | High | User has order history | 1. Click on an order number | Order details page shows items, shipping, payment info | As expected | Pass
TC-ACCT-011 | Account | Verify reorder functionality | Medium | User viewing past order | 1. Click 'Reorder' button on order | Items added to cart for repurchase | As expected | Pass
TC-ACCT-012 | Account | Verify account deletion request | Low | User is on account settings | 1. Click 'Delete Account' 2. Enter password 3. Confirm | Account deletion requested, confirmation email sent | Not tested | Blocked | Feature not available in test env

## RTM
Req ID | Requirement Description | Priority | Test Case IDs | Coverage | Status
REQ-001 | Users shall be able to register with email and password | High | TC-AUTH-001, TC-AUTH-002, TC-AUTH-003, TC-AUTH-004, TC-AUTH-005 | 100% | Covered
REQ-002 | Users shall be able to login with valid credentials | Critical | TC-AUTH-006, TC-AUTH-007, TC-AUTH-008, TC-AUTH-009 | 100% | Covered
REQ-003 | Users shall be able to logout from their account | High | TC-AUTH-011 | 100% | Covered
REQ-004 | Users shall be able to reset their password via email | High | TC-AUTH-012, TC-AUTH-013 | 100% | Covered
REQ-005 | Users shall be able to search for products | High | TC-SRCH-001, TC-SRCH-002, TC-SRCH-003, TC-SRCH-004, TC-SRCH-005 | 100% | Covered
REQ-006 | Users shall be able to filter products by category | High | TC-SRCH-006, TC-SRCH-007 | 100% | Covered
REQ-007 | Users shall be able to filter products by price range | High | TC-SRCH-008, TC-SRCH-009, TC-SRCH-010 | 100% | Covered
REQ-008 | Users shall be able to sort products | Medium | TC-SRCH-011, TC-SRCH-012, TC-SRCH-013, TC-SRCH-014 | 100% | Covered
REQ-009 | Users shall be able to filter products by brand | Medium | TC-SRCH-015, TC-SRCH-016 | 100% | Covered
REQ-010 | Users shall be able to add products to shopping cart | Critical | TC-CART-001, TC-CART-002, TC-CART-003, TC-CART-004 | 100% | Covered
REQ-011 | Users shall be able to modify cart quantities | Critical | TC-CART-005, TC-CART-010, TC-CART-011 | 100% | Covered
REQ-012 | Users shall be able to remove items from cart | High | TC-CART-006 | 100% | Covered
REQ-013 | Cart shall persist for logged in users | Medium | TC-CART-007 | 100% | Covered
REQ-014 | Users shall be able to apply coupon codes | High | TC-CART-013, TC-CART-014, TC-CART-015, TC-CART-016 | 100% | Covered
REQ-015 | Users shall be able to checkout as guest | High | TC-CHKT-002 | 100% | Covered
REQ-016 | Users shall enter valid shipping address | Critical | TC-CHKT-003, TC-CHKT-004 | 100% | Covered
REQ-017 | Users shall select shipping method | High | TC-CHKT-005, TC-CHKT-006, TC-CHKT-007 | 100% | Covered
REQ-018 | Users shall be able to pay via credit card | Critical | TC-CHKT-009, TC-CHKT-010, TC-CHKT-011, TC-CHKT-012 | 100% | Covered
REQ-019 | Order confirmation shall be displayed after purchase | Critical | TC-CHKT-013, TC-CHKT-014 | 100% | Covered
REQ-020 | Order shall appear in user's order history | High | TC-CHKT-015, TC-ACCT-009, TC-ACCT-010 | 100% | Covered
REQ-021 | Users shall be able to update profile information | Medium | TC-ACCT-001, TC-ACCT-002 | 100% | Covered
REQ-022 | Users shall be able to change password | High | TC-ACCT-003, TC-ACCT-004 | 100% | Covered
REQ-023 | Users shall be able to manage saved addresses | Medium | TC-ACCT-005, TC-ACCT-006, TC-ACCT-007, TC-ACCT-008 | 100% | Covered
REQ-024 | Users shall be able to reorder previous orders | Low | TC-ACCT-011 | 100% | Covered

## Test Execution Report
TEST EXECUTION REPORT
Execution Date: 2026-03-08
Application: shop.qaautomationlabs.com
EXECUTION SUMMARY
Total Test Cases | 90
Passed | 86
Failed | 2
Blocked | 2
Pass Rate | 95.6%
Execution Time | 16 hours
Executed By | Chinonso Nwosu
MODULE-WISE SUMMARY
Module | Total | Passed | Failed | Blocked | Pass Rate
Authentication | 15 | 14 | 0 | 1 | 93.3%
Product Search | 20 | 20 | 0 | 0 | 100%
Shopping Cart | 18 | 17 | 1 | 0 | 94.4%
Checkout | 25 | 25 | 0 | 0 | 100%
Account Management | 12 | 10 | 1 | 1 | 83.3%
DEFECT SUMMARY
Bug ID | Module | Title | Severity | Priority | Status
BUG-001 | Shopping Cart | Cart total not updating after quantity change | Critical | P1 | Open
BUG-002 | Account | Profile update shows success but doesn't save | High | P2 | In Progress
RECOMMENDATIONS
1. Critical bug BUG-001 must be fixed before release - cart functionality is core to the application
2. BUG-002 should be addressed in the next sprint as it affects user experience
3. Add more edge case tests for payment processing in next cycle
4. Consider automated regression suite for cart and checkout flows
5. Re-test blocked test cases once test environment issues are resolved
SIGN-OFF
Prepared By: | Chinonso Nwosu | Date: | 2026-03-08
Reviewed By: | _________________ | Date: | _________________
Approved By: | _________________ | Date: | _________________